## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Project architecture | 2 | 2023-07-19 | Setup of the base of the project : file tree, routing with the base url and /about , an empty Pinia store and an housing service containing functions to call the APIs
Style guide implementation | 1 | 2023-07-19 | Implemented the content of the style guide pdf in scss
Navbar | 2 | 2023-07-19 | Implemented the navigation bar, made it responsive and made the routing work. I also edited the css which wasn't complete.
House card component | 2 | 2023-07-19 | Implemented the card component template which will contain the datas retrieved from the api. I did struggle a bit to make my layout look like the model, the margins/paddings were always a bit off and the font wasn't looking the same. I eventually managed to make everything look right
Generic components | 2 | 2023-07-20 | Created new components : button, select buttons and search bar and used them for the final house listing layout.
House listing page | 2 | 2023-07-20 | Implemented the state management store and used the Pinia actions to call the api and sort/filter the results.
Random fixes | 1 | 2023-07-20 | Fixed small issues : routing, css bugs and made everything responsive
House creation page | 2 | 2023-07-20 | Made the input components and put them to the place they belong
House creation API call | 3 | 2023-07-20 | I encountered an issue due to my use of Axios, I was just putting my object formatted from the state to the body of my POST request. The server responded with a 500 error code without any other information. It did take a while before I figured out that I needed to use a FormRequest. Eventually i did convert my existing object to an adequate FormRequest.
House creation responsiveness | 1 | 2023-07-21 | Made the house creation page responsive
Random fixes / refactoring | 1 | 2023-07-21 | Spent some time making my components less redundant, fixed small issues like the house image on the cards which was not centered
Edit page | 1 | 2023-07-21 | Edited the house creation page to support house editing, using the route name, the text change and the selected house is loaded. Also added the background image like in the model.
Form validators | 3 | 2023-07-22 | Added validators to the form, I did struggle a lot with the validation of the image input, when editing the value retrieved from the server is an url to the image but with the file input I needed a File object. I did not manage to have the file object so I left the field unrequired
House detail page | 2 | 2023-07-23 | Created the detail page, I also needed to rework the house card component to fit the recommended houses. For the recommended houses I made a small recommendation algorithm to have houses with similar specs
Edit and delete | 1 | 2023-07-23 | Added the crud buttons on the listing and detail page. I also added a modal component which I used to show the delete confirmation dialogue
Form validation feedback | 2 | 2023-07-23 | I got back to the create/edit form to add more feedback for the user : each input shows an appropriate error message and styling when the value is incorrect. I also reworked the image dropzone component with a workaround for my previous issue, its validation is now handled manually.
About page | 1 | 2023-07-23 | Added the about page | x
More sorting | 1 | 2023-07-24 | Added a button to choose between ascending and descending sorting order, I also changed the third sorting parameter with the construction year. | x
Last fixes, documentation and refactoring | 2 | 2023-07-24 | Fixed every remaining issues I was aware of, commented every non obvious bit of code and refactored code.
Total amount of hours | 30